## OEL Team
6-Month Action Plan
Action Steps to Mobilize Goal | Regional or Local | Champions/ Resource Members | Completion Date | Met Goal? | Next Steps or Modifications
| Regional or District Action? | Those responsible for Action | 30-Days/ 3-Months/ 6-Months | Date completed action step | Completion of Action
Columbia County
Sources and Resources to Increase Inclusive Opportunities for Preschoolers
Priority Opportunity Area 1:Policies & Procedures
End goal (proposed solution):Have a county-wide policy that all children have the opportunity to be in a Gen Ed setting
Priority Action: An administrative meeting, ESE Director, Asst Superintendent of Curriculum to discuss issue of why we need to schedule this meeting | Local |  | 30-Days
Action 1: Create an associate meeting with all of the key admin people (VPK Coordinator and Dept, Asst Prinicipal and Director of ESE, Superintendents, ELC Executive Director, Head Start/Early Head Start Executive Director, Funding Administration) | Local |  | 30-Days |  | Organize initial summer time meeting
Action 2: Trying to get additional therapists to go into private providers if parents choose to keep children enrolled there | Local |  | 30-Days
Funding flowchart for Pre-K and VPK with more understanding of funds being distributed equally | Local |  | 30-Days
Sources and Resources to Increase Inclusive Opportunities for Preschoolers
Priority Opportunity Area 1:
End goal (proposed solution):
Sources and Resources to Increase Inclusive Opportunities for Preschoolers
Priority Opportunity Area 1:
End goal (proposed solution):
Sources and Resources to Increase Inclusive Opportunities for Preschoolers
Priority Opportunity Area 1:
End goal (proposed solution):