## Hendry
6-Month Action Plan
Action Steps to Mobilize Goal | Regional or Local | Champions/ Resource Members | Completion Date | Met Goal? | Next Steps or Modifications
| Regional or District Action? | Those responsible for Action | 30-Days/ 3-Months/ 6-Months | Date completed action step | Completion of Action
District: Hendry
Collaborating with Families and Early Childhood Agencies
Priority Opportunity Area 1: Collaboration among community preschools and district
End goal (proposed solution): Increased collaboration among community preschools and district
Action 1A: Compile a list of community preschools who enroll students with IEPs | Local |  | 30-Days | 2020-02-20 | Proceed to Action 2
Action 1B: Compile a list of community preschools who enroll students without IEPs | Local |  | 30-Days | 2020-02-20 | Proceed to Action 2
Action 2: Set a date/time for meeting with individuals from each community preschool | Local |  | 3-Months
Action 3: Review list of collaborative responsibilities of each party at scheduled meeting | Local |  | 6-Months
Action 4: Invite all stakeholders to attend IA meetings | Local |  | 3-Months
Action 5: Investigate possibility of conducting staffings at community preschools | Local |  | 3-Months
Action 6: Educate community preschool providers about child development/developmental milestones for both students with IEPs/IFSPs and typically developing peers | Local |  | 6-Months
Action 7: Provide ongoing trainings for community preschool providers (behavior, classroom management, etc.) | Local |  | 6-Months
Action 8: Discuss support available from ELC to district/community preschools (providing trainings, etc.) | Local |  | 3-Months
Sources and Resources to Increase Inclusive Opportunities for Preschoolers
Priority Opportunity Area 1:
End goal (proposed solution):
Sources and Resources to Increase Inclusive Opportunities for Preschoolers
Priority Opportunity Area 1:
End goal (proposed solution):
Sources and Resources to Increase Inclusive Opportunities for Preschoolers
Priority Opportunity Area 1:
End goal (proposed solution):