## Pasco County
6-Month Action Plan
Action Steps to Mobilize Goal | Regional or Local | Champions/ Resource Members | Completion Date | Met Goal? | Next Steps or Modifications
| Regional or District Action? | Those responsible for Action | 30-Days/ 3-Months/ 6-Months | Date completed action step | Completion of Action
Region or District: Pasco
Sources and Resources to Increase Inclusive Opportunities for Preschoolers
Priority Opportunity Area 1: Better collaborate and bridge gaps with ELCs, Community partners, and public school system to increase inclusive opportunities.
End goal (proposed solution):To bridge the gap by building strong partnerships between public and private entities that serve Pre-K students.
Action 1: Meeting with ELCs, School District, Head Start, FDLRS, and service providers in the community, to develop a plan to coordinate services and supports for students with disabilities. | Local | Elisha Perry, Carrie Colbertson, Lynn Hollingsworth, Wendy Lane, Community Teachers, Caitlin Ryan | 30-Days
Action 2: Obtain a list of preschools ELCs is serving | Local | Elisha Perry | 30-Days
Action 3: Provide a list of all community teachers and the preschools they serve to the ELCs | Local | Lynn Hollingsworth | 30-Days
Action 4: Organize meeting and invite all participant | Local | Lynn Hollingsworth | 30-Days

## Hernando County
6-Month Action Plan
Action Steps to Mobilize Goal | Regional or Local | Champions/ Resource Members | Completion Date | Met Goal? | Next Steps or Modifications
| Regional or District Action? | Those responsible for Action | 30-Days/ 3-Months/ 6-Months | Date completed action step | Completion of Action
Region or District: Hernando
Sources and Resources to Increase Inclusive Opportunities for Preschoolers
Priority Opportunity Area 1: Better collaborate and bridge gaps with ELCs, Community partners, and public school system to increase inclusive opportunities.
End goal (proposed solution):End goal (proposed solution):To bridge the gap by building strong partnerships between public and private entities that serve Pre-K students.
Action 1: Meeting with ELCs, School District, Head Start, FDLRS, and service providers in the community, to develop a plan to coordinate services and supports for students with disabilities. | Local | Elisha Perry, Danielle Loeffler, Dee Butler, Jen Stead, Denise Thompson, Carrie Culbertson, Cathy Dofka (if available) | 30-Days
Action 2: Obtain a list of preschools ELCs is serving | Local | Esisha Perry | 30-Days