## OEL Team
6-Month Action Plan
Action Steps to Mobilize Goal | Regional or Local | Champions/ Resource Members | Completion Date | Met Goal? | Next Steps or Modifications
| Regional or District Action? | Those responsible for Action | 30-Days/ 3-Months/ 6-Months | Date completed action step | Completion of Action
Region or District: Alachua County
Sources and Resources to Increase Inclusive Opportunities for Preschoolers
Priority Opportunity Area 1: Collaborative conversation/participation during Interagency Meetings (IA).
End goal (proposed solution): Present at next IA Meeting to facilitate brainstorming sessions to leverage resources among various agencies.
Action 1: Gathering information from Inclusion Retreat to share with IA Members at March meeting. | Local | Rachel Eubanks, Cynthia Kendrick, Karla Hutchinson | 30-Days
Action 2: Schedule meeting between school district and ELC to plan for IA Meeting. | Local | Rachel Eubanks | 30-Days | 2020-02-20
Action 3: Create agenda for IA Meeting | Local | Rachel Eubanks, Cynthia Kendrick, Karla Hutchinson | 30-Days
Action 4: Gather resources to distribute at IA Meeting | Local | Rachel Eubanks, Cynthia Kendrick, Karla Hutchinson | 30-Days
Action 5: Send out form to elicit feedback from meeting and determine future topics/opportunities for collaboration. | Local | Karla Hutchinson | 30-Days
Action 6: Review feedback and plan next steps to continue discussion and goals for the future. | Local | Rachel Eubanks, Cynthia Kendrick, Karla Hutchinson | 3-Months