## Big Bend
6-Month Action Plan
Action Steps to Mobilize Goal | Regional or Local | Champions/ Resource Members | Completion Date | Met Goal? | Next Steps or Modifications
| Regional or District Action? | Those responsible for Action | 30-Days/ 3-Months/ 6-Months | Date completed action step | Completion of Action
Districts in the Region: Wakulla, Calhoun, Liberty, Leon, Taylor, Gadsden, Jefferson, Madison
Collaborating with Families and Early Childhood Agencies
Priority Opportunity Area 1: Collaborate with other early childhood agencies to: Partner at activities and events, communicate through regular Pre-K interagency meetings
End goal (proposed solution): Increased participation in early childhood programs for students in our districts and access to more resources
Schedule regional interagency meetings to share information, best practices, and availible resources | Regional | TATS | 3-Months |  | Generate list of district and agency contacts
Include agencies in local events | Local | District Pre-K Contact | 30-Days |  | Communicate with district/school/community leaders to find out about upcoming events for the 20-21 school year
Develop a better method to share information and resources with parents | Regional | TATS/District Pre-K Contact | 6-Months |  | Branstorming session to develop products
Sources and Resources to Increase Inclusive Opportunities for Preschoolers
Priority Opportunity Area 1:
End goal (proposed solution):
Sources and Resources to Increase Inclusive Opportunities for Preschoolers
Priority Opportunity Area 1:
End goal (proposed solution):
Sources and Resources to Increase Inclusive Opportunities for Preschoolers
Priority Opportunity Area 1:
End goal (proposed solution):

## Calhoun
6-Month Action Plan
Action Steps to Mobilize Goal | Regional or Local | Champions/ Resource Members | Completion Date | Met Goal? | Next Steps or Modifications
| Regional or District Action? | Those responsible for Action | 30-Days/ 3-Months/ 6-Months | Date completed action step | Completion of Action
District: Calhoun
Collaborating with Families and Early Childhood Agencies
Priority Opportunity Area 1: Explore resources and make contacts with agencies
End goal (proposed solution):
Reach out to all agencies and develop working relationships | Local | Pre K Contact | 30-Days
Sources and Resources to Increase Inclusive Opportunities for Preschoolers
Priority Opportunity Area 1:
End goal (proposed solution):
Sources and Resources to Increase Inclusive Opportunities for Preschoolers
Priority Opportunity Area 1:
End goal (proposed solution):
Sources and Resources to Increase Inclusive Opportunities for Preschoolers
Priority Opportunity Area 1:
End goal (proposed solution):

## Wakulla
6-Month Action Plan
Action Steps to Mobilize Goal | Regional or Local | Champions/ Resource Members | Completion Date | Met Goal? | Next Steps or Modifications
| Regional or District Action? | Those responsible for Action | 30-Days/ 3-Months/ 6-Months | Date completed action step | Completion of Action
District: Wakulla
Collaborating with Families and Early Childhood Agencies
Priority Opportunity Area 1: Collaborate with other early childhood agencies to: Partner at activities and events, communicate through regular Pre-K interagency meetings
End goal (proposed solution):Increased participation in early childhood programs for students in our district and access to more resources
Action 1: Participate in regional interagency meetings to share information, best practices, and availible resources | Local | ESE Director and Pre K Contact | 3-Months |  | Generate list of district and agency contacts
Include agencies in local events | Local | ESE Director and Pre K Contact | 3-Months |  | Communicate with district/school/community leaders to find out about upcoming events for the 20-21 school year
Develop a better method to share information and resources with parents | Local | ESE Director and Pre K Contact | 6-Months |  | Branstorming session to develop products
Sources and Resources to Increase Inclusive Opportunities for Preschoolers
Priority Opportunity Area 1:
End goal (proposed solution):
Sources and Resources to Increase Inclusive Opportunities for Preschoolers
Priority Opportunity Area 1:
End goal (proposed solution):
Sources and Resources to Increase Inclusive Opportunities for Preschoolers
Priority Opportunity Area 1:
End goal (proposed solution):

## Liberty
6-Month Action Plan
Action Steps to Mobilize Goal | Regional or Local | Champions/ Resource Members | Completion Date | Met Goal? | Next Steps or Modifications
| Regional or District Action? | Those responsible for Action | 30-Days/ 3-Months/ 6-Months | Date completed action step | Completion of Action
District: Liberty
Sources and Resources to Increase Inclusive Opportunities for Preschoolers
Priority Opportunity Area 1: Find other funding sources in order to provide more inclusive opportunities
End goal (proposed solution):
Investigate school readiness | Local | Pre K Contact | 30-Days
Sources and Resources to Increase Inclusive Opportunities for Preschoolers
Priority Opportunity Area 1:
End goal (proposed solution):
Sources and Resources to Increase Inclusive Opportunities for Preschoolers
Priority Opportunity Area 1:
End goal (proposed solution):
Sources and Resources to Increase Inclusive Opportunities for Preschoolers
Priority Opportunity Area 1:
End goal (proposed solution):