## Regional Name
6-Month Action Plan
Action Steps to Mobilize Goal | Regional or Local | Champions/ Resource Members | Completion Date | Met Goal? | Next Steps or Modifications
| Regional or District Action? | Those responsible for Action | 30-Days/ 3-Months/ 6-Months | Date completed action step | Completion of Action
Region or District: North Florida (Clay, Nassau, St. Johns)
Sources and Resources to Increase Inclusive Opportunities for Preschoolers
Priority Opportunity Area 1: Building Relationships and Collaboration
End goal (proposed solution): Common opportunities to collaborate on a regular schedule (ie: 3 times a year)
Action 1: Set the date & location | Regional | ELC/ECS | 3-Months
Action 2: Invite participants | Local |  | 30-Days
Action 3: School Districts contacts need to discuss/ "get buy in" from appropriate district staff | Local | PreK contacts for each district | 30-Days
Action 4: Follow up meeting with TATs and regional to discuss intial "buy in" status, obtain more information from organizations | Regional | TATS and PreK contacts | 3-Months
Action 5: ELC/ECS to gather information on local providers for each district (Special Needs Rate Status, providers open to district support, common training opportunities) | Regional | ELC/ECS | 3-Months

## St Johns
6-Month Action Plan
Action Steps to Mobilize Goal | Regional or Local | Champions/ Resource Members | Completion Date | Met Goal? | Next Steps or Modifications
| Regional or District Action? | Those responsible for Action | 30-Days/ 3-Months/ 6-Months | Date completed action step | Completion of Action
Region or District: St Johns
Sources and Resources to Increase Inclusive Opportunities for Preschoolers
Priority Opportunity Area 1: Building Relationships and Collaboration
End goal (proposed solution): Common opportunites to collaborate on a regular schedule
Action 1: Possible restructure IA meetings | Local | PreK contact and TATS | 3-Months
Action 2: Investigage resources with our various PreK departments within district | Local | PreK contact | 30-Days

## Nassau
6-Month Action Plan
Action Steps to Mobilize Goal | Regional or Local | Champions/ Resource Members | Completion Date | Met Goal? | Next Steps or Modifications
| Regional or District Action? | Those responsible for Action | 30-Days/ 3-Months/ 6-Months | Date completed action step | Completion of Action
Region or District: Nassau
Sources and Resources to Increase Inclusive Opportunities for Preschoolers
Priority Opportunity Area 1:Building Relationships and Collaboration
End goal (proposed solution): Common opportunites to collaborate on a regular schedule
Action 1: Investigage resources with our various PreK departments within district | Local | PreK contact | 30-Days
Action 2: Meet with Director of ESE for "buy in" | Local | PreK contact | 30-Days

## Clay
6-Month Action Plan
Action Steps to Mobilize Goal | Regional or Local | Champions/ Resource Members | Completion Date | Met Goal? | Next Steps or Modifications
| Regional or District Action? | Those responsible for Action | 30-Days/ 3-Months/ 6-Months | Date completed action step | Completion of Action
Region or District:
Sources and Resources to Increase Inclusive Opportunities for Preschoolers
Priority Opportunity Area 1:Building Relationships and Collaboration
End goal (proposed solution): Common opportunites to collaborate on a regular schedule
Action 1: Meet with ESE Director to discuss vision and passion. | Local | ESE PreK contact | 30-Days
Action 2: Meet with ASD program specialist to disucss inclusion model pilot at a local elementary (sucesses and overcoming obstacles) | Local | ESE PreK contact | 30-Days
Action 3: Get with local agencies from IA meeting to disucss supports they have to offer community, how we can supporting children through joined forces. Have conversations of vulnerability. (No one agency has the magical fairy dust.) | Local | ESE PreK contact | 3-Months
Action 4: Review district resources, current make up of returning students and where we can inittate more inclusive opportunties for FALL. | Local | ESE PreK contact | 6-Months
Action 5: Develop a plan to get to know local providers | Local | ESE PreK contact and ESE director | 6-Months
Action 6: | Local |  | 30-Days
Action 7: | Local |  | 30-Days
Action 8: | Local |  | 30-Days
Action 9: | Local |  | 30-Days
Action 10: | Local |  | 30-Days