## Regional Name
6-Month Action Plan
Action Steps to Mobilize Goal | Regional or Local | Champions/ Resource Members | Completion Date | Met Goal? | Next Steps or Modifications
| Regional or District Action? | Those responsible for Action | 30-Days/ 3-Months/ 6-Months | Date completed action step | Completion of Action
Region or District: Flagler/Volusia
Sources and Resources to Increase Inclusive Opportunities for Preschoolers
Priority Opportunity Area 1:
End goal (proposed solution):
Action 1: Regional action planning meetings. Introduce problem solving/action planning in Interagency agendas, create opportunity for electronic participation | Regional | Roxie, Nancy, Amy , Rose Marie | 3-Months
Action 2: Set up meeting with Teri Evans (St. Johns) re Conscious Discipline implementation | Regional | Roxie, Nancy, Kim, Rose Marie | 30-Days

## Volusia
6-Month Action Plan
Action Steps to Mobilize Goal | Regional or Local | Champions/ Resource Members | Completion Date | Met Goal? | Next Steps or Modifications
| Regional or District Action? | Those responsible for Action | 30-Days/ 3-Months/ 6-Months | Date completed action step | Completion of Action
Region or District: Volusia
Collaborating with Families and Early Childhood Agencies
Priority Opportunity Area 1:Assemble champions to collaborate on how best to create innovative opportuities, systems and programs.
End goal (proposed solution): Increase collaboration around strategies to support inclusion
Action 1: Invite community EL programs and families to district training opporutnities at start of school year. FDLRS as funding source. | Local | Melissa, Patty, Lauren, Nathalie, Nancy | 6-Months
Action 2: Design model for family events based on one that has been successful, identify what it will take to get families to attend training (Family Renew model) | Local | Denise, Sandy, Lauren, Patty and Nathalie | 3-Months
Action 3: Book Conscious Discipline Training for all (private programs, families, district staff) in August, emphasize paralell process. Follow up , check in for fidelity in implementation | Local | Roxie,Holly Christian, Erica Garris, ELC Coaches | 30-Days
Action 4: CARD help with PATH | Local | Roxie | 3-Months
Action 5: Establish agenda for and have meeting with VCS Superintendent | Local | Nancy, DJ, Volusia ESE team | 3-Months
Action 6: Assist families needing care for babies transitioning out of Early Steps not yet in VCS programs for 3 year olds. Bridge gap between bdays/summer and start of school year programs. | Local | Melissa, Nathalie, Nancy | 30-Days

## Flagler
6-Month Action Plan
Action Steps to Mobilize Goal | Regional or Local | Champions/ Resource Members | Completion Date | Met Goal? | Next Steps or Modifications
| Regional or District Action? | Those responsible for Action | 30-Days/ 3-Months/ 6-Months | Date completed action step | Completion of Action
Region or District: Flagler
Sources and Resources to Increase Inclusive Opportunities for Preschoolers
Priority Opportunity Area 1:
End goal (proposed solution):
Action 1: CARD help with PATH | Local | Roxie | 30-Days