## LevyGilchristDixie
6-Month Action Plan
Action Steps to Mobilize Goal | Regional or Local | Champions/ Resource Members | Completion Date | Met Goal? | Next Steps or Modifications
| Regional or District Action? | Those responsible for Action | 30-Days/ 3-Months/ 6-Months | Date completed action step | Completion of Action
Regions in the District: Levy, Gilchrist, Citrus and Dixie
Professional Development: Preparing Personnel
Priority Opportunity Area 1: Tri-County PK Summer Institute
End goal (proposed solution): PK teachers in Levy, Gilchrist, and Dixie will participate in a two-day summer institute, with collaboration between the school districts, OEL, FDLRS, and TATS to engage in high-quality professional development around identified areas of need.
Action 1: Select dates for PK Summer Institute. | Regional | Team Members | 30-Days
Citrus County will share Frog Street Curriciculum Maps with Levy County. | Regional | Sharon Harker | 30-Days
Citrus County will share progress monitoring tool (ESGI) with other districts. | Regional | Sharon Harker | 30-Days
Action 4: Select topics for 2-day institute based on the following ideas: Integrating Standards Phonolgoical Awareness (2 CEUs)-OEL, Instructional Implications of VPK Assessment (2 CEUs)-OEL, Scaffolding (2 CEUs)-OEL, Rock Your Classroom-TATS, Make and Take, Math--Sets and Sorting, Counting and Operations (3 CEUs each)-OEL | Regional |  | 30-Days
Action 5: Email Chris (TATS) about what trainings she can offer, including Rock Your Classroom. | Regional | Laura Klock | 30-Days
Action 6: Set up planning meeting and schedule for Summer Institute with FDLRS, TATS, and School District staff. | Regional | Salley Martin | 3-Months
Sources and Resources to Increase Inclusive Opportunities for Preschoolers
Priority Opportunity Area 1:
End goal (proposed solution):
Sources and Resources to Increase Inclusive Opportunities for Preschoolers
Priority Opportunity Area 1:
End goal (proposed solution):
Sources and Resources to Increase Inclusive Opportunities for Preschoolers
Priority Opportunity Area 1:
End goal (proposed solution):