## OEL Team
6-Month Action Plan
Action Steps to Mobilize Goal | Regional or Local | Champions/ Resource Members | Completion Date | Met Goal? | Next Steps or Modifications
| Regional or District Action? | Those responsible for Action | 30-Days/ 3-Months/ 6-Months | Date completed action step | Completion of Action
Region or District: Osceola
Collaborating with Families and Early Childhood Agencies
Priority Opportunity Area 1: To bridge the gap between public schools and private providers
End goal (proposed solution): To establish an inter-agency collaboration plan
Action 1: Schedule a meeting between both the school district and ELC | Local | DCPS and ELC | 30-Days
Action 2: Meet to identify the collaborative needs of both (School District and ELC) | Local | DCPS and ELC | 3-Months
Action 3: Resource study by each agency and compile results of resources offered by the school district and ELC | Local | DCPS and ELC | 3-Months
Action 4: Meet to discuss results of resource study and work on establishing an interagency collaboration plan | Local | DCPS and ELC | 6-Months