## OEL Team
6-Month Action Plan
Action Steps to Mobilize Goal | Regional or Local | Champions/ Resource Members | Completion Date | Met Goal? | Next Steps or Modifications
| Regional or District Action? | Those responsible for Action | 30-Days/ 3-Months/ 6-Months | Date completed action step | Completion of Action
Region or District: Santa Rosa
Sources and Resources to Increase Inclusive Opportunities for Preschoolers
Priority Opportunity Area 1::Collaboration: Partnering with district and non-district stakeholders to discover, share and maximize existing resources.
End goal (proposed solution): Increase Inclusion Opportunites for ESE Pre-K Students
Action 1: Establish a district planning team to include local ELC and school district. | Local | T. Colemanm and L. Templeton | 30-Days
Action 2: ESE Department to reassume oversight and decision making responsibility of ESE Pre-K Units | Local | D. Anderson | 6-Months
Action 3: Investigate the possibility of providing itinerate services to local private providers | Local | T. Coleman L. Templeton D. Anderson | 3-Months
Sources and Resources to Increase Inclusive Opportunities for Preschoolers
Priority Opportunity Area 2: Professional Development: Preparing Personnel for Inclusion
End goal (proposed solution): Increase Inclusion and Academic Skillset of ESE Pre-K and VPK Personnel
Action 1: Professional Development focused on behavior interventions for Community VPK and School Based Providers | Local | L. Templeton, ELC and District Behavior Team | 6-Months
Action 2: Professional Development focused on Pre-K standards and implementation to bridge school readiness gap to school based ESE Pre-K personnel. | Local | L. Templeton, OEL, TATS, District ELA Department (V. Avis), K. Patrick | 6-Months
Action 3: Professional Development to Blended Classroom Teachers on the Blended Inclusion Model | Local | T. Coleman, L. Templeton, E. Toms, ELC and TATS | 6-Months