## OEL Team
6-Month Action Plan
Action Steps to Mobilize Goal | Regional or Local | Champions/ Resource Members | Completion Date | Met Goal? | Next Steps or Modifications
Sarasota | Regional or District Action? | Those responsible for Action | 30-Days/ 3-Months/ 6-Months | Date completed action step | Completion of Action
Region or District: Sarasota
Sources and Resources to Increase Inclusive Opportunities for Preschoolers
Priority Opportunity Area 1: Bridge the gap between public and private providers. Investigate resources and opportunities within the school district and community agencies in order to collaborate to provide a continuum of services and more inclusive settings.
End goal (proposed solution): Offer at least one inclusive opportunity in the community.
Action 1: Meet with the school district and ELC internally in the district. | Local | ELC and School district personnel | 30-Days
Action 2: Interagency meeting between school district and ELC. | Local | ELC and School district personnel | 3-Months
Action 3: Interagency meeting between school district, Early Steps and ELC. | Local | ELC and School district personnel | 3-Months
Action 4: Develop a plan to accommodate the stakeholders involved in the district. | Local | ELC and School district personnel | 6-Months